## Stakeholder Register
Stakeholder Register — [Project Name]
Stakeholder Name | Role / Title | Team / Function | Interest in Project | Influence Level | Decision Authority | Engagement Expectation | Communication Preference | Key Concerns | Actions Needed
Sarah Chen | Project Sponsor | Executive | High — budget and strategic alignment | High | Final sign-off on scope | Weekly 1:1 briefing | Email + steering deck | Delivery timeline slippage | Confirm milestone dates by Sprint 2
Marcus Webb | IT Director | Technology | Medium — infrastructure and security | High | Technical architecture approval | Bi-weekly sync | Teams call | Data sovereignty and cloud costs | Provide cloud architecture review by Phase 3
Priya Nair | Operations Lead | Business Operations | High — process redesign impacts her team | Medium | Approves process flows | Weekly stand-up attendance | Confluence page + email | User adoption and training timeline | Assign UAT lead from her team by Sprint 8
James Kato | End User Rep (Senior Clerk) | Claims Operations | High — daily system user | Low | Provides UAT sign-off | Monthly demo attendance | Demo + feedback form | System usability and reduced manual steps | Participate in 3 discovery workshops

## RACI Matrix
RACI Matrix — [Project Name]
Deliverable | Responsible | Accountable | Consulted | Informed | Notes
Stakeholder Map | BA Lead | Project Sponsor | IT Director, Ops Lead | All stakeholders | Review in kickoff week
Functional Specification | BA Lead | IT Director | Operations Lead, Dev Lead | Project Sponsor | Sign-off required before backlog build
User Stories | BA Lead | Product Owner | Operations Lead, Dev Lead | QA Lead | DoR gate before sprint entry
UAT Plan | BA Lead | Operations Lead | QA Lead, End Users | Project Sponsor, IT Director | Distribute 2 weeks before UAT start
Go-Live Decision | Project Manager | Project Sponsor | IT Director, Ops Lead | All stakeholders | CAB approval required

## Power-Interest Grid
Power-Interest Grid — [Project Name]
Quadrant | Stakeholder | Strategy | Example Action
Manage Closely (High Power / High Interest) | Project Sponsor, IT Director | Regular 1:1s, include in all key decisions, get sign-off early | Weekly briefing deck; escalate risks immediately
Keep Satisfied (High Power / Low Interest) | CFO, Legal, Compliance | Periodic updates, no surprises, escalate risks before they escalate them | Monthly one-page status email; flag budget changes early
Keep Informed (Low Power / High Interest) | Operations Lead, End Users, QA Lead | Regular updates, involve in UAT and demos, incorporate feedback | Sprint demo invites; feedback forms after each demo
Monitor (Low Power / Low Interest) | Vendor Partners, Other Departments | Newsletter-style updates, available for questions on request | Quarterly update email; include in go-live announcement