## User Stories
User Stories — [Project Name]
Story ID | Epic | Title | As a... | I want to... | So that... | AC 1 (Happy Path) | AC 2 (Error / Validation) | AC 3 (Edge Case) | Business Rules | Dependencies | Priority | Story Points | Sprint | Status
US-001 | EPIC-01 E-Filing | Attorney submits DOR with inline validation | an attorney | submit a Declaration of Readiness form with field-level validation | invalid or incomplete filings are prevented before submission — reducing NIGO rate by 60% | Given all required fields are complete, When attorney clicks Submit, Then system accepts filing and displays confirmation number within 5 seconds | Given 'Date of Injury' field is blank, When attorney clicks Submit, Then field is highlighted red and error message 'Date of Injury is required' is shown | Given a DOR is already pending for the same case, When attorney submits, Then system warns 'Pending DOR exists (filed [date]). Proceed?' | BR-001, BR-002, BR-007 | US-002, EPIC-01 | Must | 5 | Sprint 3 | Not Started
US-002 | EPIC-01 E-Filing | Case number typeahead search | an attorney | start typing a case number and see matching suggestions | I can find the correct case without knowing the exact format — reducing search time from 5 min to under 30 seconds | Given attorney types 3+ characters, When search input is triggered, Then system returns top 5 matching cases within 1 second | Given no matches exist, When attorney completes typing, Then system displays 'No cases found — check case number format' with format guide link | Given attorney has no access to a case, When it appears in search, Then it is shown greyed out with 'No access' tooltip | BR-003 | None | Must | 3 | Sprint 3 | Not Started
US-003 | EPIC-02 Scheduling | Judge views daily hearing calendar | a judge | see my full hearing calendar for the day with case summaries on a single screen | I can prepare for hearings in 15 minutes instead of 45 minutes across 3 separate systems | Given judge logs in, When dashboard loads, Then today's hearings are displayed in chronological order with case number, parties, and hearing type | Given a hearing is cancelled after calendar loads, When judge refreshes, Then cancelled hearing is shown with strikethrough and cancellation reason | Given judge has no hearings today, When dashboard loads, Then screen displays 'No hearings scheduled for today' with next hearing date | BR-012, BR-015 | US-004, EPIC-02 | Must | 8 | Sprint 4 | Not Started