## RTM
Requirements Traceability Matrix — [Project Name]
Source ID | Requirement | Category | Priority | Source Doc | Epic ID | Story ID | Rule IDs | Design Ref | Test Case IDs | UAT Case IDs | Defect IDs | Status | Sprint | Release | Comments
REQ-001 | System shall allow attorneys to submit DOR forms electronically with inline validation | FR | Must | RFP §3.4, Exhibit B INT-26 | EPIC-01 | US-001, US-002 | BR-001, BR-002 | Figma: DOR-V2 | TC-001, TC-002, TC-003 | UAT-001, UAT-002 |  | In Progress | Sprint 3 | R1.0 | Core e-filing requirement
REQ-002 | System shall auto-populate party names from existing case data | FR | Must | RFP §3.5 | EPIC-01 | US-004 | BR-003 | Figma: DOR-V2 §4 | TC-010 | UAT-005 |  | Not Started | Sprint 4 | R1.0 | Reduces manual entry by 80%
REQ-003 | System response time shall be under 2 seconds for all search operations | NFR | Must | RFP §7.2 | EPIC-01 | US-002 |  | Tech Spec §9.1 | TC-050, TC-051 |  |  | Not Started | Sprint 5 | R1.0 | Perf test required in staging
REQ-004 | System shall provide judges with a single-screen daily hearing summary | FR | Must | RFP §4.1, Workshop 2 output | EPIC-02 | US-003, US-005 | BR-012, BR-015 | Figma: JUDGE-DASH-V1 | TC-020, TC-021 | UAT-010 |  | Not Started | Sprint 4 | R1.0 | Judge sign-off required on wireframe
REQ-005 | All DOR submissions shall generate an immutable audit trail | NFR | Must | RFP §8.3, Compliance §2 | EPIC-01 | US-006 | BR-020 | Tech Spec §12 | TC-060 |  |  | Not Started | Sprint 5 | R1.0 | Legal review needed

## Coverage Summary
Coverage Summary
Category | Total Requirements | In Backlog | Test Coverage | UAT Coverage | Gaps
Functional (FR) | 18 | 18 | 14 | 8 | 4 FRs missing test cases — see REQ-012, 015, 017, 019
Non-Functional (NFR) | 7 | 7 | 5 | 3 | Performance tests pending staging environment
Integration (INT) | 5 | 5 | 3 | 1 | INT-04, INT-05 not yet in test scope
Data Migration (DM) | 3 | 2 | 1 | 0 | REQ-DM-003 not in backlog — add to Sprint 6
TOTAL | 33 | 32 | 23 | 12 | 1 requirement not in backlog; 10 missing test coverage