## Sprint Readiness
Sprint Readiness Review — [Sprint Name]
Story ID | Title | Epic | Sprint | Scope Clear | ≥3 ACs | Rules Linked | Dependencies Known | Data Defined | UX / Process Ref | Testable | Estimable | No Open Blockers | Approval Received | OVERALL STATUS | Gaps / Actions
US-001 | Attorney submits DOR with validation | EPIC-01 | Sprint 3 | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | SPRINT READY
US-002 | Case number typeahead search | EPIC-01 | Sprint 3 | ✓ | ✓ | ✓ | ✗ | ✓ | ✓ | ✓ | ✓ | ✗ | ✓ | NOT SPRINT READY | 1) Dependency on Search API spec not confirmed with IT (owner: Marcus Webb, due: Mon) 2) BA to resolve: what happens when attorney has no access rights to matching case?
US-003 | Judge views daily hearing calendar | EPIC-02 | Sprint 3 | ✓ | ✓ | ✗ | ✓ | ✗ | ✓ | ✓ | ✗ | ✓ | ✗ | NOT SPRINT READY | 1) BR-012 in Draft status — needs Legal sign-off 2) Data fields for case summary not defined (owner: BA Lead) 3) Story points TBD — needs Tech Lead input 4) Wireframe JUDGE-DASH-V1 pending design review
US-004 | Auto-populate party names | EPIC-01 | Sprint 4 | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | SPRINT READY | Scheduled Sprint 4 — not yet in sprint