## UAT Feedback
UAT Feedback Log — [Project Name]
# | Tester | Date | Cycle | Story / Req Ref | Description | Expected | Actual | Severity | Evidence Link | Status | Owner | Fix Sprint | Retest Result | Sign-off
1 | Priya Nair | 2026-05-12 | UAT Cycle 1 | US-001 | When I submit the DOR with all fields complete, the confirmation number displays but the email notification does not arrive | Email notification within 5 minutes of submission | Confirmation screen shown correctly but no email received after 20 minutes | High | Screenshot: UAT-EVD-001.png | In Progress | Dev Lead — Arjun Shah | Sprint 9 | Pending
2 | James Kato | 2026-05-12 | UAT Cycle 1 | US-002 | Typeahead search returns correct results but does not work when I type the case number with dashes (e.g. ADJ-1234567) | Search works with or without dashes | No results returned when dash format is used — only works without dashes | Medium | Screenshot: UAT-EVD-002.png | Not Started | Dev Lead — Arjun Shah | Sprint 9 | Pending
3 | Priya Nair | 2026-05-13 | UAT Cycle 1 | US-003 | Judge calendar displays correctly for today but the navigation arrows to move to next/previous day do not work | Clicking → advances calendar by one day | Arrows do not respond to clicks; no error message displayed | High | Screen recording: UAT-EVD-003.mp4 | Not Started | Dev Lead — Arjun Shah | Sprint 9 | Pending
4 | Sarah Chen | 2026-05-14 | UAT Cycle 1 | US-001 | Performance: DOR submission page takes 8–12 seconds to load on the first visit | Page loads in under 2 seconds per NFR-001 | Initial load 8–12 sec; subsequent loads 1–2 sec | Medium | Network trace: UAT-EVD-004.har | Not Started | Tech Lead — Ravi Kumar | Sprint 9 | Pending