## Change Log
Change Request Log — [Project Name]
CR ID | Date | Requested By | Description | Reason / Justification | Impacted Stories | Impacted Tests | Schedule Impact | Cost Impact (hrs) | Option A (Full) | Option B (Simpler) | Recommendation | Approval Status | Owner | Resolution Date
CR-001 | 2026-04-08 | Priya Nair — Operations Lead | Add a 'Related Cases' panel to the case detail view showing all cases linked by common parties | Judges frequently need to know if a party has other pending cases to avoid conflicting orders. Currently requires 3 manual lookups. | US-003, US-005, US-011 | TC-020, TC-025 | +2 sprints (4 weeks), delays Sprint 14–15 features | 160 | Build full Related Cases panel with party-linked case list, status, and hearing dates (4 weeks, 160 hrs) | Add hyperlink from party name to existing party search results (1 day, 8 hrs — solves 80% of use case) | Option B — 80% of business value at 5% of cost. Full panel deferred to Phase 2 with usage data. | Pending Approval | Sarah Chen | 2026-04-15
CR-002 | 2026-04-10 | Sarah Chen — Project Sponsor | Add multi-language support (Spanish) for the e-filing portal | 3% of attorney filers are Spanish-speaking; complaints received from bar association. | US-001 through US-010 (all e-filing stories) | All e-filing test cases | +4 sprints (8 weeks), significant backlog re-work | 320+ | Full Spanish translation of all e-filing screens, labels, errors, and emails (8 weeks) | Add language toggle for error messages only on DOR form — most critical pain point (3 days) | Defer full translation to Phase 2 post go-live. Build i18n framework now (Option B) at low cost. | Under Review | Sarah Chen | 2026-04-17