## Risk & Issue Log
Risk and Issue Log — [Project Name]
ID | Type | Description | Category | Likelihood (1-5) | Impact (1-5) | Risk Score (L×I) | Owner | Mitigation / Action | Status | Due Date | Linked Stories
R-001 | Risk | Key subject matter expert (Priya Nair) leaving before Phase 3 requirements are finalised | Stakeholder | 3 | 5 | 15 | BA Lead | 1) Complete and baseline all Phase 3 requirements by Sprint 5 2) Identify and onboard backup SME from Operations team by Sprint 3 3) Document all workshop decisions in Confluence same day | Active | 2026-04-30 | REQ-001 through REQ-018
R-002 | Risk | Legacy CAMS integration API documentation is incomplete — actual behaviour may differ from spec | Technical | 4 | 4 | 16 | IT Director — Marcus Webb | 1) BA to conduct reverse-engineering session with CAMS system owner by Sprint 4 2) Build integration adapter with configuration-driven mapping to accommodate variations 3) Add 5-day buffer to Sprint 6 for integration defect resolution | Active | 2026-05-15 | INT-001, INT-002
R-003 | Issue | UAT environment provisioning delayed by 2 weeks — impacting UAT start date | Environment | 5 | 4 | 20 | IT Director — Marcus Webb | ESCALATED: IT Director to provide revised environment readiness date by EOD Friday. Contingency: conduct UAT on pre-production with data snapshot if staging unavailable. | Escalated | 2026-05-01 | All UAT cases
R-004 | Risk | End users resistant to new e-filing process — adoption risk at go-live | Change Management | 3 | 3 | 9 | Project Manager | 1) Include 3 end-user reps in sprint demos from Sprint 3 2) Run 2-day training programme 2 weeks before go-live 3) Assign super-users in each district office as go-live support | Active | 2026-06-01 | US-001 through US-010
R-005 | Risk | Statutory deadline calculation business rule has unresolved legal ambiguity for holiday edge cases | Compliance | 2 | 5 | 10 | Legal / BA Lead | Legal to provide written confirmation of holiday calculation rules by Sprint 5. Interim: implement conservative calculation (longest permissible window) until confirmed. | Active | 2026-05-20 | BR-020, US-008