## MoSCoW
MoSCoW Prioritisation — [Project Name]
Story ID | Title | Epic | MoSCoW | Business Value | Rationale | Dependencies | Sprint
US-001 | Attorney submits DOR with inline validation | EPIC-01 | Must | Core statutory requirement — e-filing not functional without this | Legal mandate — cannot go live without | None | Sprint 3
US-002 | Case number typeahead search | EPIC-01 | Must | Prevents most common filing error (wrong case) | 40% of current rejections are wrong case number | US-001 | Sprint 3
US-003 | Judge views daily hearing calendar | EPIC-02 | Must | Eliminates 30 min/day prep time across 150 judges | Phase 1 core capability — judges will not adopt without this | None | Sprint 4
US-006 | Audit trail for DOR submissions | EPIC-01 | Must | Legal compliance — non-negotiable | HIPAA and state compliance requirement | US-001 | Sprint 5
US-007 | Attorney dashboard with filing history | EPIC-01 | Should | High user value — reduces call centre queries | Valuable but not blocking go-live | US-001, US-002 | Sprint 6
US-011 | Bulk DOR upload for large firms | EPIC-01 | Could | Useful for 5% of high-volume filers | Addresses niche need; manual upload works for most | US-001 | Sprint 9
US-014 | Multi-language support (Spanish) | EPIC-01 | Won't | Addresses 3% of filers | Phase 2 scope — build i18n framework now; translate post-launch | US-001 through US-010 | Phase 2

## WSJF
WSJF Prioritisation — [Project Name]
Story ID | Title | Cost of Delay (1-10) | Risk Reduction (1-10) | Opportunity Enablement (1-10) | Job Size (1-10) | WSJF Score (÷ Job Size) | Rank | Sprint | Rationale
US-001 | DOR inline validation | 10 | 9 | 9 | 5 | 5.6 | 1 | Sprint 3 | Highest CoD — legal mandate; blocks all other e-filing
US-002 | Case typeahead search | 8 | 7 | 8 | 3 | 7.7 | 2 | Sprint 3 | Very high score — small job, high value, unblocks filing accuracy
US-006 | Audit trail | 9 | 10 | 7 | 4 | 6.5 | 3 | Sprint 5 | Compliance risk reduction drives high score despite medium job size
US-003 | Judge calendar | 7 | 5 | 9 | 8 | 2.6 | 4 | Sprint 4 | High value but large job size (complex dashboard) lowers WSJF
US-007 | Attorney filing history | 5 | 3 | 7 | 4 | 3.8 | 5 | Sprint 6 | Good value story; not blocking go-live