## Test-Story Mapping
Test Cases vs Stories Coverage — [Project Name]
Story ID | Story Title | AC ID | AC Description | Test Case ID | Test Scenario | Pass / Fail | Gap Notes
US-001 | DOR submission with validation | AC-001-1 | Happy path: all fields complete → submission accepted with confirmation | TC-001 | Submit complete DOR — verify confirmation number displayed within 5 sec | Pass
US-001 | DOR submission with validation | AC-001-2 | Error: blank required field → inline error shown, submission blocked | TC-002 | Submit DOR with blank Date of Injury — verify red highlight + error message | Pass
US-001 | DOR submission with validation | AC-001-3 | Edge: duplicate DOR for same case → warning with Proceed/Cancel | TC-003 | Submit DOR for case with existing pending DOR — verify warning dialog | Fail | DEFECT: warning displayed but Proceed button submits without logging override reason — BR-002 violation
US-001 | DOR submission with validation | AC-001-4 | ⚠ MISSING TEST — email notification within 5 min of submission |  | TC not yet written |  | GAP: UAT-001 revealed email notifications not working. No automated test exists for notification pathway. Add TC-004 to test suite Sprint 9.
US-002 | Case typeahead search | AC-002-1 | Happy path: 3+ characters typed → 5 suggestions within 1 second | TC-010 | Type 'ADJ123' in case number field — verify 5 suggestions appear in <1 sec | Pass
US-002 | Case typeahead search | AC-002-2 | Error: no matches found → helpful error + format guide link | TC-011 | Type 'ZZZZZ' in case number field — verify no-results message + format link | Pass
US-002 | Case typeahead search | AC-002-3 | Edge: no-access case in results → greyed out with 'No access' tooltip | TC-012 | Log in as attorney without case access — verify restricted case appears greyed | Not Run | Blocked: test data for restricted case not yet set up — owner: QA Lead, due Sprint 9